## Slide 1
Project Management
Type period
Type period
Type period
Type period
Type task
Type task
Type task
Type task
Type task

## Slide 2
OVERVIEW
PROJECT PLANNING and SCHEDULING
The purpose of this lesson is to provide you with the knowledge to plan and supervise drafting and surveying activities for construction projects.
Type text
Type text
Type text
Type text
Type text
Type text
Type text

## Slide 3
LEARNING OBJECTIVES
T.L.O.
Provided a project mission, written project specifications, finished design drawings, a completed bill of materials, a scientific calculator, a computer, software applications, a printer, and the references, implement project planning methods detailing all personnel, equipment, and materials necessary to accomplish the mission while establishing a defined duration for each subtask and the overall project / operation and graphically depict the schedule per the references. (1361-SRVY-2004)

## Slide 4
LEARNING OBJECTIVES
E.L.O.
(1). Given written project specifications, and blank writing paper, and references, develop an activities list per the FM 5-412. (1361-SRVY-2004a
(2). Given written project specifications, a completed activity list, and blank writing paper, and references, create a logic diagram per the FM 5-412. (1361-SRVY-2004b)
(3). Given written project specifications, a completed activity list, a completed logic diagram, scientific calculator, and blank activity estimate sheets, and references, estimate project activity durations per the FM 5-412. (1361-SRVY-2004c)

## Slide 5
LEARNING OBJECTIVES
E.L.O.
(4). Given written project specifications, a completed activity list, completed activity estimate sheets, a computer, and automated software application, and references, create a Gantt chart per the FM 5-412.
(1361-SRVY-2004d)
(5). Given written project specifications, a completed activity list, completed activity estimate sheets, a computer, and automated software application, and references, complete a logic diagram per the FM
5-412. (1361-SRVY-2004e)

## Slide 6
LEARNING OBJECTIVES
E.L.O.
(6). Given written project specifications, a completed activity list, a completed logic diagram, completed activity estimate sheets, scientific calculator, and completed activity estimate sheets, and references, create a completed project schedule per the FM 5-412. (1361-SRVY-2004f)
(7). Given a completed project schedule, computer, and automated software application, and references, automate a project schedule per the FM 5-412. (1361-SRVY-2004g)

## Slide 7
METHOD
AND
MEDIA
LECTURE, DEMONSTRATION, PRACTICAL APPLICATION
SLIDE PRESENTATION
DRY-ERASE BOARD
HANDOUTS

## Slide 8
EVALUATION
CLOSE-BOOK
WRITTEN / PERFORMANCE
IRFs

## Slide 9
SAFETY /
CEASE TRAINING BRIEF
FIRE
TORNADO

## Slide 10
QUESTIONS
?

## Slide 11
CRITICAL PATH METHOD (CPM)
CPM is a form of analysis that is used for planning, scheduling, and controlling construction activities for a project from start to finish.
The CPM requires a formal, detailed listing of all work related activities that make up the project.
Also referred to as:
  Construction Management
  Project Planning and Scheduling
  Critical Path Analysis

## Slide 12
PRELIMINARY PLANNING
Preliminary planning is a quick overall picture of the project and the capacity of the unit to accomplish it.
Serves as a guide for detailed planning.
Includes site recon, preliminary material and equipment estimates, and procurement of critical items.

## Slide 13
DETAILED PLANNING
Develops an accurate estimation of work activities, materials, man-hours, and equipment requirements needed from start to finish.
Detailed planning includes:
  Reviewing project specifications and drawings.
  Detailed estimates of resources.
  Scheduling work activities.
  Submitted in the form of a Gantt chart, Pert chart, Activity-on-the-Arrow logic diagram, or Activity-on-the-Node logic diagram.

## Slide 14
Job Directive Format
The job directive is the tasking of a unit to perform construction tasks, and draw needed materials to complete the project assigned.
Job directives vary in form and content. They are issued in one of two ways:
  Verbally for simple projects.
  Written for more complex projects.

## Slide 15
Stages of Detail
Job directives can be in any one of three stages of detail:
  Contain detailed plans and specifications. The more stable the conditions are, the more detailed the job directive becomes.
  May simply refer to standardized drawings, or automated software programs already published.
  May require preparation of complete plans and project specifications to be approved by higher headquarters.

## Slide 16
Job Directive Information
Mission: Exact assignment with all necessary details.
Location: May be given, or left to the unit to select.
Time: Starting time and/or required completion date.
Manpower: Additional manpower that is available.
Equipment: Additional equipment that is available.

## Slide 17
Job Directive Information, cont.
Materials: Source of and authority to request materials.
Priorities: Single priority for the whole project, or separate priorities for various portions of the project.
Reports: Any required reports. (i.e. Weekly status report)
Special Instructions: Any additional information pertaining to the job that is requested.

## Slide 18: In what two forms may job directives be issued? In military construction, the planning process is divided into what two stages?
?
Notes: ANSWER: They may be issued either verbally or in writing.
ANSWER: Preliminary planning and detailed planning.

## Slide 19
ACTIVITY LISTS (Brainstorming)
An activities (task) list is a complete listing of all required
work activities that must be performed from start to finish.
An activity list can be brief, or as detailed as need be. The guiding factor to how much detail that is required is dictated by size and complexity of the project.
An activity list must be developed mentally and on paper to determine actual activities and their interrelationships to each other.
The most difficult step is your ability to think logically, and make a mental picture of the project in your mind. Brainstorming is needed with the assistance of the 1349, 1371 and 1361 Chief's, and the Project Officer.

## Slide 20
PROJECT:
One lane gravel road, 1500 feet long, leading to a concrete storage pad that is 32’-0” x 32’-0” in size.
Activities
“Topo” project site Establish road grades
Lay gravel Set road alignments
Order gravel Place concrete forms
Clear roadway Clear pad site
Prefabricate forms Create project drawings
Layout pad batter boards Excavate pad footings
Pour concrete Cure concrete
Check pad elevations Check Road grades
Remove forms Perform “As-built”
ROUGH ACTIVITIES LISTING

## Slide 21
Sequencing Activities
After you have developed your rough activity list in no specific order, you must now put the activities into a "logical" sequence to be performed. The finished activity list is broken down as follows:
  “Activity Number” Column
  “Activity” Column
  "Immediately Proceeded By" (IPB) Column

## Slide 22
Types of Activities
There are five types of activities associated
with the development of a finished activities list. Keeping these activities in mind will help you in your logical thinking to develop the activity list
on paper.
  Starting activities.
  Preceding activities.
  Concurring activities.
  Succeeding activities.
  Lagging activities.
Notes: ANSWER: They may be issued either verbally or in writing.
ANSWER: Preliminary planning and detailed planning.

## Slide 23
Sample Finished Activities List
Activity
Number Activity __ IPB
5 "Topo" project site None
10 Create project drawings 5
15 Order gravel None
20 Prefabricate forms None
25 Clear roadway 10
30 Set road alignments 25
35 Establish road grades 30
40 Check road grades 35
45 Lay gravel 15,40
50 Clear pad site 10
55 Layout pad batter boards 50
60 Excavate pad footings 55
65 Check pad elevations 60
70 Place concrete forms 20,65
75 Pour concrete 70
80 Cure concrete 75
85 Remove forms 80
90 Perform "as-built" 45,85

## Slide 24
DEMONSTRATION
“Going to Morning Formation”

## Slide 25: What is the process called to develop your activities list? : What are the five types of activities that are kept in mind when developing a finished activities list?
?
Notes: ANSWER: Brainstorming.
ANSWER: Starting, Proceeding, Succeeding, Concurring, and Lagging activities.

## Slide 26
10 Min
Break!

## Slide 27
PLANNING DIAGRAMS
The most important part of the CPM is the planning diagram. The planning diagram graphically shows the interrelationship between project activities.
  It provides a visual blueprint of the work activities that must be performed during construction.
  There are four types of diagrams that can be created. Each serves a specific purpose.

## Slide 28
GANTT CHART
Also known as a bar chart.
Gantt charts are "time" oriented.
Activities are graphically shown on a calendar time scale, used primarily for small projects.
Bars show an activities duration in its entirety, regardless of its dependency on other activities.
Effortless to construct, and are brief in format.

## Slide 29
ID
Task Name
1
Topo project site
2
Create project drawings
3
Order gravel
4
Prefabricate forms
5
Clear roadway
6
Set road alignments
7
Establish road grades
8
Check road grades
9
Lay gravel
10
Clear pad site
11
Layout pad batterboards
M
T
W
T
F
S
S
M
T
W
T
F
S
S
M
T
W
T
F
S
S
April 7
April 14
April 21
GANTT CHART

## Slide 30
ID
Task Name
1
TEC 1-99
2
TEC Core
3
Marine Unique
4
TEC 5-99
5
TEC Core
6
Marine Unique
10/6/98
2/1/99
TEC 1-99
10/6/98
1/8/99
TEC Core
1/11/99
2/1/99
Marine Unique
11/3/98
3/1/99
TEC 5-99
11/3/98
2/5/99
TEC Core
2/8/99
3/1/99
Marine Unique
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
4, 1998
Qtr 1, 1999
Qtr 2, 1999
Qtr 3, 1999
GANTT CHART

## Slide 31
GANTT CHART DISADVANTAGES
Does not give you the ability to visualize the exact progress of the project.
Anticipate delays or problems soon enough to correct them.
Does not show detailed sequence of activities.
Does not show "critical activities".
Does not show precise effect of a delay or failure to complete an activity on time.

## Slide 32
PERT CHART DIAGRAM
The Program Evaluation and Review Technique (PERT) addresses probability, and is "event" oriented.
This type of logic diagram is used primarily for research and development projects.

## Slide 33
PERT CHART

## Slide 34
Activity-On-The-Arrow Format
More complex in its creation.
Tendency to lead to confusion when trying to interpret it.
Least desirable format to use because of these factors.

## Slide 35
ACTIVITY-ON THE-ARROW CHART

## Slide 36
Activity-On-The-Node Format
Eliminates confusion, and allows you to adjust for problems that may arise during the construction of the project.
AON format is "activity" oriented.
This is the primary format used for planning military construction, and especially used for large projects.

## Slide 37
Activity-On-The-Node Uses
Construction planning
Maintenance planning
Project Design
Military combat task planning
Logistics planning

## Slide 38
AON Advantages
Reduces risk of overlooking essential tasks.
Provides a blueprint for long-range planning.
Shows activity interrelationships.
Focuses attention on critical activities.
Allows you to make timely decisions.
Allows you to manage manpower, material, and equipment resources more effectively.

## Slide 39
AON Disadvantages
The AON format does not solve engineering problems that may occur.
Does not make planning decisions for you.
Does not provide anything substantial to the actual construction of the project itself.

## Slide 40
ACTIVITY-ON-THE-NODE

## Slide 41
LOGIC DIAGRAM ELEMENTS
After the activity relationships are identified, they are applied to a logic diagram. The standard format for a logic diagram is the "Activity-on-the-Node".
The four basic elements are:
Activity Nodes
Start Nodes
Finish Nodes
Precedence Arrows

## Slide 42
ACTIVITY NODE

## Slide 43
PRECEDENCE ARROWS

## Slide 44
START AND FINISH NODES
20
Duration in days

## Slide 45: What type of planning diagram is “event” oriented? What type of planning diagram is “time” oriented? What type of planning diagram is “activity” oriented?
?
Notes: ANSWER: Pert chart.
ANSWER: Gantt chart.
ANSWER: AOA and AON diagrams.

## Slide 46
LOGIC DIAGRAMS
Shown as a Critical Path Method (CPM) logic diagram.
Shows accurate, timely, and easily understood picture of the whole project.
Easier to plan, schedule, and manage the sequence of required work activities.
Graphically shows the interrelationship of each work activity as they relate to the completion of the whole project.

## Slide 47
CPM DIAGRAM LOGIC RULES
Which activities start at the beginning of the project? (Starting)
Which activities must be finished before the start of another? (Preceding)
Which activities can start or finish at the same time as another? (Concurring)
Which activities cannot begin until another is finished? (Succeeding)

## Slide 48
DEMONSTRATION
“Going to Morning Formation”

## Slide 49
PRACTICAL
EXERCISE

## Slide 50: What logic rules are used to create a logic diagram? What must all finishing nodes tie into?
?
Notes: ANSWER: Starting, Proceeding, Succeeding, Concurring, and Lagging activities.
ANSWER: Finish node.

## Slide 51
10 Min
Break!

## Slide 52
ACTIVITY ESTIMATES
Estimating each activities required resources and duration times.
Estimated resources are:
  Materials
  Personnel
  Equipment
  Man-hours
  Equipment-hours

## Slide 53
MATERIAL ESTIMATES
Work Items
Materials
Quantities
Waste Factors
Total Material Requirements
Bills of Materials

## Slide 54
EQUIPMENT/PERSONNEL ESTIMATES
Work Items. (Activities)
Material Quantities. (Units of work)
Work Rate. (Man-hour Tables)
Standard Work Effort (Labor). (Quantity x Work Rate)
Efficiency Factor. (Represented as a Percentage)
Troop Effort (Total Labor Hours). (Standard Effort / Efficiency)
Duration (Hours, Days, Weeks, or Months).
(Troop Effort / Crew Size)

## Slide 55
DURATIONS
Durations are calculated based on:
  Amount of Material Handled
  Amount of effort put into using manpower
Duration Guidelines:
  Increasing equipment or Personnel = Reduced duration time of Activity.
  Decreasing equipment or Personnel = Increased duration time of Activity.
  Increasing length of workday = Reduced duration time of Activity.
  Decreasing length of workday = Increased duration time of Activity.
  Working on the weekend = Reduced duration time of the entire project.

## Slide 56: What are the two types of estimates? What effect does increasing equipment quantities have on the duration of an activity?
?
Notes: ANSWER: Material and Equipment/manpower estimates.
ANSWER: It reduces its duration time.

## Slide 57
EARLY/LATE EVENT TIMES
After all duration's have been computed, you are now able to calculate each activities Early and Late event times. (Forward Pass and Backward Pass)
  Early Start (ES): The earliest time a activity can logically start.
  Early Finish (EF): The earliest an activity can finish without delaying follow on activities. (ES + Duration)
  Late Finish (LF): The latest an activity can finish without delaying the entire project.
  Late Start (LS): The latest time an activity can start without delaying the entire project. (LF - Duration)

## Slide 58
Activity
Number Activity IPB Duration
5 “Topo” project site None 2 days
10 Create project drawings 5 2 days
15 Order gravel None 6 days
20 Prefabricate forms None 1 day
25 Clear roadway 10 2 days
30 Set road alignments 25 1 day
35 Establish road grades 30 1 day
40 Check road grades 35 2 days
45 Lay gravel 15,40 2 days
50 Clear pad site 10 1 day
55 Layout pad batter boards 50 1 day
60 Excavate pad footings 55 2 days
65 Check pad elevations 60 1 day
70 Place concrete forms 20,65 1 day
75 Pour concrete 70 1 day
80 Cure concrete 75 6 days
85 Remove forms 80 1 day
90 Perform “As-built” 45,85 2 days
ACTIVITY LIST WITH ESTIMATED DURATION'S

## Slide 59
CRITICAL PATH
& CRITICAL ACTIVITIES
After completing the event times, you can determine the "critical path" of the project and all of the "critical activities" by simple observation using the following guidelines:
  The ES for an activity is the same as its LS.
  The EF for an activity is the same as its LF.

## Slide 60
DEMONSTRATION
“EARLY/LATE EVENT TIMES”

## Slide 61
PRACTICAL
EXERCISE

## Slide 62: What are some of the types of resources that must be estimated for an activity? What is the term that is used to calculate the early event times for a project? What is the term that is used to calculate the late event times for a project?
?
Notes: ANSWER: Material, personnel and equipment quantities, and man-hours and equipment hours.
ANSWER: Forward pass.
ANSWER: Backward pass.

## Slide 63
10 Min
Break!

## Slide 64
EARLY START SCHEDULES
An early start schedule, when joined with the logic diagram, graphically shows all of the planning information that is needed to manage the construction project from start to finish.
Any activity not on the "Critical Path" will contain some float. Float is any extra time that is available to complete an activity beyond its actual duration, without effecting the entire project.

## Slide 65
EARLY START SCHEDULE FORMAT

## Slide 66
FLOAT
Total Float (TF): The entire amount of time that an activity can be delayed without delaying the entire project completion time.
  TF = LS - ES or LF - EF
Interfering Float (IF): Time that is available to delay an activity without delaying the projects entire completion time, but may delay the start of one or more non-critical activities.
  IF = LF -ES of following activity. (Use the smallest ES time)
Free Float (FF): Time that is available to delay an activity without delaying the start of any other activity, or the entire projects completion time.
  FF = TF - IF

## Slide 67: Early Start Schedule Plotting
Start by listing all activity numbers and their succeeding activities.
Draw time brackets: Length is equal to LF-ES. (This will include total float if any)
Note: ES times for starting activities will be day 1. All other ES will begin on the morning of the succeeding day.
Label resource quantities in each appropriate time bracket. Only label the blocks for the activity’s normal duration.

## Slide 68
RESOURCE ABBREVIATIONS
SQUAD = SQ | 7-TON = 7T
SCRAPER = SC | DOZER = DZ
BACKHOE LOADER = BL | EXCAVATOR = EX
COMPACTOR = CP | SHEEPS FOOT = SF
SURVEY CREW = EA | HMMWV = HV
DRAFTSMAN = EA | TRAM = TR
GRADER = GD | DUMP TRUCK= DT

## Slide 69: Early Start Schedule Plotting (Cont.)
Interfering Float: When plotting IF work right to left starting at the ending bracket, shown as a “X”. IF will be plotted first. Any remaining blank/open blocks will be Free Float.
Free Float: FF will fall automatically into position after the IF is marked.
Note: All finishing activities will only have FF and that the critical path will NOT have any float.
The final step is to total all resources for each day and list them at the bottom of the schedule.

## Slide 70
DEMONSTRATION
“EARLY START SCHEDULE”

## Slide 72
10 Min
Break!

## Slide 73
PRACTICAL
EXERCISE

## Slide 74: What is float? What is interfering float? What is free float?
?
Notes: ANSWER: Float is any extra time that is available to complete an activity beyond its actual duration without effecting the entire project duration.
ANSWER: The time that is available to delay an activity without delaying the entire projects completion time, but delaying an activity into interfering float will delay the start of one or more non-critical activities later.
ANSWER: Time that is available to delay an activity without delaying the start of any other activity, or the projects’ completion time.

## Slide 75
10 Min
Break!

## Slide 76: MICROSOFT PROJECT
Automated Program
  Planning and Scheduling
Does not make decisions for you!
  You provide inputs
    Activities
      Resources
      Duration
    Project
      Beginning
      Finish

## Slide 77: MS PROJECT – INITIAL SETTINGS
Date, Time, Duration Settings
  TOOLS Menu
    OPTIONS Dialogue Box
      View Tab
        Date Format
      Calendar Tab
        Day of the week work begins
        Time of the day work begins and ends
        Hours work / day and week
      Schedule Tab
        DAYS – set Activity Duration, time unit format
        HOURS – set Work Duration
          NOTE: Slack time = 0; allows MS Proj ect to calculate
          FLOAT TIMES

## Slide 78: MS PROJECT – INITIAL SETTINGS
Date, Time, Duration Settings, cont.
  Tools Menu
    Change Working Time
      Set Working Days
      Set Non-Working Days
        Weekends automatically considered
        Holidays

## Slide 79: MS PROJECT – RESOURCE SETTINGS
T/O (Manpower)
T/E (Equipment)
  VIEW Menu
    RESOURCE SHEET
      Resource Name
      Resource Initials
      Maximum Units
        Unit, Company, Platoon, Section
    GANTT CHART

## Slide 80: MS PROJECT – ACTIVITY INFORMATION
PROJECT ACTIVITY INFORMATION INPUT
  VERTICAL DISPLAY DIVIDER
    Pick, Drag all the way to the right to view entire Activity sheet
  Type Name of first Activity
    Left Arrow Key
      Column
        Duration
      Column
        Starting Date
      Column (Left Arrow Key x2)
        Predecessors

## Slide 81: MS PROJECT – ACTIVITY INFORMATION, cont.
PROJECT ACTIVITY INFORMATION INPUT
    Resource information – leave blank
    Repeat previous procedures for the remaining Activities in your list.
      Skip “STARTING DATES”, they will be automatically calculated due to IPB
    INSERT Menu
      Resource Assignment Dialogue box
        Type of Resource
          Quantity
            Units
      Repeat for all Activities
        Close

## Slide 82: MS PROJECT – EDITING PLANNING DIAGRAMS
Activity Information Inputs = Automatic Planning
Diagram Creation
    GANTT Chart
      Pick, Drag Vertical Divider all the way to the left so the entire GANTT Chart can be viewed
      Pick FORMAT Menu
        Select Bar Styles Option
          NAME Column
            Pick PROGRESS
              Pick CUT ROW (eliminates clutter for printout)
              Do not delete TASK
      INFORMATION Display Format
        Pick TASK Name
          Pick TEXT Tab

## Slide 83: MS PROJECT – EDITING PLANNING DIAGRAMS, cont.
    PERT Chart
      Chart created is not in logical sequence
      Drag and Drop Activity Node so the Precedence Arrow Logically connect each node
        Begin Arranging
          Starting Activities first then remaining Activities to the last
          Note: PERT Chart does not have a Start or Finish Node

## Slide 84: MS PROJECT – PROJECT REPORTS
    Supplements Planning Diagrams with:
      Pick VIEW in the Menu Bar
        RESOURCE USAGE
        RESOURCE GRAPHS
          REPORTS
            OVERVIEW
              Top-Level Tasks
              Critical Tasks
              Working Days
          CURRENT ACTIVITIES
            Unstarted Tasks
          ASSIGNMENTS
            Who does what
            Who does when

## Slide 85
DEMONSTRATION

## Slide 86
PRACTICAL
EXERCISE

## Slide 87: How does Microsoft Office Project calculate float times? Does a PERT Chart have a Start and Finish Node?
?
Notes: ANSWER: By inputting ZERO (0) in the Slack Time upon setting up the Microsoft Office Project file.
ANSWER: No.

## Slide 88: SUMMARY
Critical Path Method in project planning and scheduling
Activities List
  Brainstorming
  Sequencing
CPM Logic Diagram
Activity Resources
Early Start Schedule
MS Project Production